## Example Timeline
Draft Ward Print Plan
Key
Design
Print | Item | Ward Intro Leaflets | Team Labour Newsletter | Targetted postal vote DM POSTED | Ward Election Address | Targetted DM Hand Delivered | GOTPV Card | GOTV Cards | Total | Door Drop EXAMPLE
Delivery | Spec | A5 2pp | A5 4pp | A4 4pp | A5 2pp | A4 2pp | DL 2pp | DL 2pp |  | A5 2pp
| Unit | 0.024167 | 0.029833 | 0.654 | 0.024167 | 0.162 | 0.04428 | 0.0443 |  | 0.1
| Indicative Cost | 145 | 179 | 490.5 | 145 | 81 | 44.28 | 132.9 | 1217.68 | 650
| QTY | 6000 | 6000 | 750 | 6000 | 500 | 1000 | 3000 | 23250 | 6500
| Notes |  |  | Includes BRE envelope |  |  |  | 1000 of 3x designs |  | Whole postcode sectors only
Turnaround from artwork ordered |  | 3-4 working days | 3-4 working days | 5 working days | 3-4 working days | 3-4 working days | 3-4 working days | 3-4 working days |  | 4 weeks
October | w/c 3rd | Photos and Stories
| w/c 10th | Photos and Stories
| w/c 17th | Design on Labour Connects
| w/c 24th | Sign off and order on Labour Connects
| w/c 31st | Print
November | w/c 7th | Delivery
| w/c 14th | Delivery
| w/c 21st | Delivery
| w/c 28th | Delivery
December | w/c 5th | Delivery
| w/c 12th | Delivery | Photos and Stories
| w/c 19th | Delivery | Photos and Stories
| w/c 26th |  | Design on Labour Connects
January | w/c 2nd |  | Sign off and order on Labour Connects
| w/c 9th |  | Print
| w/c 16th |  | Delivery | [6 empty] | Initial Enquiry
| w/c 23 |  | Delivery | [6 empty] | Book In
| w/c 30 |  | Delivery |  | Photos and Stories |  |  |  |  | Design and Payment
February | w/c 6th |  | Delivery |  | Photos and Stories |  |  |  |  | Print
| w/c 13th |  | Delivery | Design on Labour Connects | Design on Labour Connects | Photos and Stories |  |  |  | Deliver to Royal Mail
| w/c 20th |  | Delivery | Sign off and Order on Labour Connects | Sign off and order on Labour Connects | Photos and Stories |  |  |  | Deliver to postcode sector
| w/c 27th |  | Delivery | Print and Delivery | Print | Design on Labour Connects
March | w/c 6th |  |  |  | Delivery | Sign off and order on Labour Connects
| w/c 13th |  |  |  | Delivery | Print | Design on Labour Connects
| w/c 20th |  |  |  | Delivery | Delivery | Sign off and order on Labour Connects
| w/c 27th |  |  |  | Delivery |  | Print
April | w/c 3rd |  |  |  | Delivery |  | Delivery
| w/c 10th |  |  |  | Delivery |  |  | Design on Labour Connects
| w/c 17th |  |  |  | Delivery |  |  | Sign off and order on Labour Connects
| w/c 24th | [6 empty] | Print
May | ELECTION WEEK | [6 empty] | Delivery